## Sheet1
BUG REPORT-Jan M
Version of the application: Ver name |  | Environment details : Windows 11 |  | Identified By: Namratha P V
Reported To: Pradeep K C |  | Module name: Home Page |  | Date: 12/10/2023
Bug Id | Test Id | Bug Description | Severity | Priorty | Screenshot | Status
Def_JM_HP_01 |  | About option hyperlink in hamburger button is not working | Minor | High | https://drive.google.com/file/d/1ibKNqhWhYs_JU9CfpcX6RLjw8Xb6zWwp/view?usp=drive_link | New
Def_JM_HP_02 |  | Home option hyperlink in hamburger button is not working | Minor | High | https://drive.google.com/file/d/1bT0qeCzcwnhZJgOT7VdwnVgfR0RD_Xhn/view?usp=drive_link | New
Def_JM_HP_03 |  | Address option hyperlink in hamburger button is not working | Minor | High | https://drive.google.com/file/d/1oGBcUg3OCXqi-OrEMiM9WxI8aNfk3UZg/view?usp=drive_link | New
Def_JM_HP_04 |  | Bio option hyperlink in hamburger button is not working | Minor | High | https://drive.google.com/file/d/196P_JJfwqFEaz-jtoQH_pb2ghD7ZSIkB/view?usp=drive_link | New
Def_JM_HP_05 |  | Mobile number hyperlink below Book an appoinment section is not working | Major | Very High | https://drive.google.com/file/d/1fxPm_DC8yQVdFfJKwANjn4Xzye34V_cJ/view?usp=drive_link | New
Def_JM_HP_06 |  | "View all services" hyperlink is misspelled as "veiw all services" | Trivial | Low | https://drive.google.com/file/d/1yzBDcQiXUutfBUoSDJdh5tzMWgBoj7EM/view?usp=drive_link | New
Def_JM_HP_07 |  | "Veiw all services" hyperlink is not redirecting to our services | Minor | High | https://drive.google.com/file/d/1yzBDcQiXUutfBUoSDJdh5tzMWgBoj7EM/view?usp=drive_link | New
Def_JM_HP_08 |  | View Bio hyperlink in the Our surgeon section is not working | Minor | High | https://drive.google.com/file/d/1xwufOz1XPh3eJK1OQpk6d_O0LPTi9qvc/view?usp=drive_link | New
Def_JM_HP_09 |  | LinkedIn icon in Instagram section (Footer section) is not redirecting to LinkedIn | Major | Very high | https://drive.google.com/file/d/1U9SURiPfaGdF9_gjp2fMBBRgIUFAHBhS/view?usp=drive_link | New
Def_JM_HP_10 |  | Twitter icon in Instagram section (Footer section) is not redirecting to Twitter | Major | Very high | https://drive.google.com/file/d/1aph2eCwJk0hOcz-0B-MawW1l-fvrY7t5/view?usp=drivesdk | New
Def_JM_HP_11 |  | WhatsApp icon in Instagram section (Footer section) is not redirecting to WhatsApp | Major | Very high | https://drive.google.com/file/d/18aRPO9NG_4P0Gx01JgnSopWr59Zrbt3Z/view?usp=drivesdk | New
Def_JM_HP_12 |  | Google+ icon in Instagram section (Footer section) is not redirecting to Google+ | Major | Very high | https://drive.google.com/file/d/14c5bl2HGTYnIr1FcDBGKR7hzlxHV48bt/view?usp=drivesdk | New
Def_JM_HP_13 |  | Google+ icon in Instagram section (Footer section) should be removed as Google+ is discontinued | Trivial | Low | https://drive.google.com/file/d/14c5bl2HGTYnIr1FcDBGKR7hzlxHV48bt/view?usp=drivesdk | New
Def_JM_HP_14 |  | Instagram section (Footer section) should be renamed as social media | Trivial | Low | https://drive.google.com/file/d/1UYlXpIQTeuNdcdOriOapgM6Yp-y1t_rb/view?usp=drivesdk | New
Def_JM_HP_15 |  | Site content not displayed properly in mobile view | Critical | Very high | https://drive.google.com/file/d/1_I7fsfuHJsVlp4KTRBBaYnpdWvBj_Sda/view?usp=drivesdk | New
Def_JM_HP_16 |  | Security Certificate of the site is invalid/not present | Critical | Very High | https://drive.google.com/file/d/1kQMZweMzVemgX_aYILfDVh1_t0HP6Rs3/view?usp=drivesdk | New